## Income
Sr No. | Subject | Refrence | From | To | Date | Receiving Date | Source File
1 | NOCs for Sub Projects under KPCIP | LGE&RDD/KPCIP/2022/3233-3238 | D.T PMU-KPCIP | CEO WSSCA | 2022-06-30 | 2022-07-04
2 | Notification of Grievances Redressal Committee for KPCIP sub Projects | 4048-50 | Add. Deputy Commissioner Atd | CEO WSSCA | 2022-09-20 | 2022-09-09
3 | Pursuance on Construction Of Water tanks through private Negotiation | KPCIP/PMU/LGE&RDD/2022-23/127-131 | P.D KPCIP | Deputy Commissioner Atd | 2022-07-21 | 2022-07-26
4 | Physical Activities On Sub-Projects " Green Initiatives" Under KPCIP | LGE&RDD/KPCIP/2022/135-137 | D.T PMU-KPCIP | CEO WSSCA | 2022-07-22 | 2022-07-25
5 | No Objection Certificate (NOC's) For Sub-Projects Under KPCIP | LGE&RDD/KPCIP/2022/186-190 | D.T PMU-KPCIP | CEO WSSCA | 2022-07-25 | 2022-07-26
6 | Detail Presentation Regarding Green Initiative Projects | LGE&RDD/KPCIP/2022/200-210 | D.T PMU-KPCIP | CEO M/S CSC & CEO WSSCA | 2022-07-26 | 2022-07-27
7 | Meeting of Meeting On Progress Review At KPCIP-PMU | KPCIP/PMU-Admin/2022-23/2014-2023 | P.D KPCIP | CEO WSSCA | 2022-09-21 | 2022-10-03
8 | Meeting of Project Staff Recruitment Committee | KPCIP/Admin/General/2022-23/2253-2268 | Director Finanace & Admin PMU KPCIP | CEO WSSCA | 2022-10-12
9 | Nomination of Focal Persons For Disbursement committee | KPCIP/PMU/LGE&RD/Compliance/2022-23/2397-2408 | Director Compliance PMU-KPCIP | CEO WSSCA | 2022-10-20 | 2022-10-24
10 | Minutes of the Disbursement Committee For The Abbottabad City | PMU-KPCIP/IVS-RP/Fund/2480-2491 | Director Compliance PMU-KPCIP | CEO WSSCA | 2022-10-25 | 2022-10-26
11 | Minutes of the 1st Disbursement Committee Of The KPCIP | KPCIP/Compliance/S.General/2022-23/2586-2597 | Director Compliance PMU-KPCIP | CEO WSSCA | 2022-10-27 | 2022-10-31
12 | Non-Cooperation of Mr. Qasim Ali (M&E Officer),CIU-KPCIP ,WSSC Abbottabad | KPCIP/Admin/CIUs/04(A)/2022-23/2630-2638 | Admin & Procurement Officer PMU-KPCIP | CEO WSSCA | 2022-10-27 | 2022-10-31
13 | Notification of The Engineers Of The Project As per Sub-Clauses 1.1.2.4 & 3.1 Of GCC/PCC | KPCIP/Admn/S.General/2022-23/2598-2607 | P.D KPCIP | CEO WSSCA | 2022-10-27 | 2022-11-22
14 | Submission of Records Apropas Contractor's Personnel And Equipments In Accordance With Sub-Clause 6.9 & 6.10 of GCC/PCC> | KPCIP/PMCSC/RE/ATD/Lot-1/003 | RE (Green & Urban Spaces) | CEO M/S JHK & CEO WSSCA | 2022-11-01 | 2022-11-02
15 | Submmission of Detail Time Programme/ Working Schedule in Accordance With Sub-Clause 8.3 of GCC/PCC | KPCIP/PMCSC/RE/ATD/Lot-1/002 | RE (Green & Urban Spaces) | CEO M/S JHK & CEO WSSCA | 2022-11-01 | 2022-11-02
16 | Submission of Contractor's Representative In Accordance with Sub-Clause 4.3 of GCC/PCC | KPCIP/PMCSC/RE/ATD/Lot-1/004 | RE (Green & Urban Spaces) | CEO M/S JHK & CEO WSSCA | 2022-11-01 | 2022-11-03
17 | Submission of Site Specific Environmental Manangment Plan (SSEMP) And Site Specific Health and Safety Management Plan In Accordance with Sub-Clause 4.18 & 6.7 of GCC/PCC | KPCIP/PMCSC/RE/ATD/Lot-1/001 | RE (Green & Urban Spaces) | CEO M/S JHK & CEO WSSCA | 2022-11-01 | 2022-11-02
18 | Appointment of Dispiute Board Under Sub Clause 20.2 of GCC/PCC | KPCIP/DT/GS/PR/2022-23/3033-42 | D.T PMU-KPCIP | CEO WSSCA | 2022-11-11 | 2022-11-14
19 | Request for Submission of Insurance in Accordance with Clause 18 [UNSURANCE] of GCC/PCC | KPCIP/PMCSC/RE/ATD/Lot-1/015 | RE (Green & Urban Spaces) | CEO M/S JHK | 2022-11-11 | 2022-11-15
20 | #3 Sample of Soil for Modified Proctor Test (AASHTO T-99 & T-180) | KPCIP/PMCSC/RE/ATD/Lot-1/2022/016 | RE (Green & Urban Spaces) | Departement Of Civil Engg Comsats ATD/CEO WSSCA | 2022-11-15 | 2022-11-16
21 | OCB/KPCIP/CW-01: Clearance of Impediments In the Stated Project. | KPCIP/PMCSC/RE/ATD/Lot-1/017 | RE (Green & Urban Spaces) | CEO WSSCA | 2022-11-16 | 2022-11-16
22 | Nomination of Focal Persons During visit of ADB Mission Of Different Districts of KPK | KPCIP/Admn/S.General | P.D KPCIP | CEO WSSCA | 2022-11-21
23 | Notification of The Engineer(s) Pursuant to Sub-Clause 1.1.2.4 and 3.1 of GCC/PCC | KPCIP/PMCSC/PMU/005 | CEO M/S CEC | P.D KPCIP | 2022-12-01 | 2022-12-14
24 | Meeting of Project Staff Recruitment Committee | KPCIP/Admin/2022-23/2783-2799 | D.T PMU-KPCIP | CEO WSSCA | 2022-12-07 | 2022-11-10
25 | Appointment of Dispiute Board Under Sub Clause 20.2 of GCC/PCC | KPCIP/DT/GS/PR/2022-23/5027-36 | D.T PMU-KPCIP | CEO WSSCA | 2022-12-13 | 2022-12-14
26 | Provison of Technical Sanction (TS) of Sub-Projects Under KPCIP LGE&RDD | KPCIP/DT/GS/PR/2022-23/5015-26 | D.T PMU-KPCIP | CEO WSSCA | 2022-12-13 | 2022-12-14
27 | Relocation of CIU Office Abbottabad | KPCIP/Admin/S.General/2022-23/5118-21 | Procurement & Admin Officer PMU-KPCIP | CEO WSSCA | 2022-12-16
28 | KPCIP -02: Institutional Review And Capacity Building Consultant. Meeting of Technical Committee | KPCIP/DT/Misc/2022-23/5099-5113 | WATSAN Specilist | CEO WSSCA | 2022-12-16
29 | Offical Use of Vehicles Of City Imlementation Unit (CIU) KPCIP | KPCIP/Admin/S.General/2022-23/5214-17 | Procurement & Admin Officer PMU-KPCIP | CEO WSSCA | 2022-12-21 | 2022-12-23
30 | Contractor [M/S Matracon-JTE (JV) Request for Extension of Time On Advance Payment Guarantee Under Sub-Clause 14.2 Of PCC | KPCIP/DT/STP/MN/2022-23/5249-63 | D.T PMU-KPCIP | CEO WSSCA | 2022-12-22 | 2022-12-23
31 | Delivery of Training Program-Human Resource (Workforce) Management (training code 3.1 | KPCIP/Misc/2022-23/5241-48 | Urban Development Specialist PMU-KPCIP | CEO WSSCA | 2022-12-22
32 | KPCIP Development of Urban/green Spaces and Parks LOT-1 Pedestrianization of Old City Bazar & Development of Sherwan Hill Park | 674-75/21/5 | AAd. Chief Engr Pesco hazara-1,Circle | CEO PESCO Peshawar | 2023-01-19 | 2023-01-19
33 | Request for Issuance of Umrella NOC in Respect for Exection of Sub Project Under KPCIP | 1203/TMA | TMO TMA ATD | CEO WSSCA | 2023-02-07
34 | Design Facilities in Front of Sarafa Bazar | KPCIP/PMCSC/RE/ATD/Lot-1/041 | RE (Green & Urban Spaces) | CEO WSSCA | 2023-03-13
35 | Interm Payment Certificate No.1 (CW-01,Lot-01) | KPCIP/DT/UGS/ATD/2023-24/8893-8898 | WATSAN Specilist | CEO WSSCA | 2023-05-12 | 2023-05-15
36 | Abnormal Delay in Release Of IPC # 1 | Reliable-JHK/KPCIP/L-1/AA/80 | P.M JHK | P.D KPCIP | 2023-06-21
37 | Abnormal Delay in Release Of IPC # 1 (Reminder #1)- | Reliable-JHK/KPCIP/L-1/AA/82 Remind-1 | P.M JHK | P.D KPCIP | 2023-07-05 | 2023-07-05
38 | Minutes of the meeting Regarding review of Kpcip Project in Abbottabad | 42/4/AD/ACD/CHD(Dev)/7358-63 | Commissioner Hazara | CEO WSSCA | 2023-07-10 | 2023-07-21
39 | Interm Payment Certificate No.1 (CW-01,Lot-01) | KPCIP/DT/UGS/ATD/2023-24/163-169 | WATSAN Specilist | RE PMCSC KPCIP | 2023-07-10 | 2023-07-21
40 | Design Facilities in Front of Sarafa Bazar | KPCIP/PMCSC/RE/ATD/Lot-1/101 | RE (Green & Urban Spaces) | CEO WSSCA | 2023-07-14
41 | Notification of Base Index Rates Adjustment for Changes in Cost Under Provisions of Sub-Clause 13.8, GCC | KPCIP/DT/UGS/ATD/2023-24/33-345 | WATSAN Specilist | CEO WSSCA | 2023-07-18
42 | Submission Of Escalation Paymnet Certificate (EPC) No.01 LOT.1 | Reliable-JHK/KPCIP-01/ABT-LOT-1/67 | P.M JHK | RE (Green & Urban Spaces) | 2023-07-19
43 | Provision Of Technical Sanction (TS) of Awarded Sub-project Under KPCIP | KPCIP/PMCSC/RE/ATD/Lot-1/104 | RE (Green & Urban Spaces) | CEO WSSCA | 2023-07-19
44 | Submission Of Escalation Paymnet Certificate No 21: Price Adjsutment No.01 | KPCIP/PMCSC/RE/ATD/Lot-1/105 | RE (Green & Urban Spaces) | P.D KPCIP | 2023-07-21
45 | Request for Nomination of suitable Personnel of TMA for Joint Oversight of Urban/Green Spaces Project | 4977/TMA | TMO TMA ATD | CEO WSSCA | 2023-07-21
46 | Non-Compliance with Sub-Clause 8.3 (Programme) | KPCIP/PMCSC/RE/ATD/Lot-1/107 | RE (Green & Urban Spaces) | P.M JHK | 2023-07-27 | 2023-08-02
47 | Submission of Price Adjustment No.01 | KPCIP/DT/UGS/ATD/2023-24/519-523 | WATSAN Specilist | CEO WSSCA | 2023-07-31 | 2023-08-02
48 | Bunching of electrical cables in Bazar | KPCIP/PMCSC/RE/ATD/Lot-1/108 | RE (Green & Urban Spaces) | CEO WSSCA | 2023-07-31 | 2023-08-02
49 | Suspension of Work Without Prior Notice | KPCIP/PMCSC/RE/ATD/Lot-1/110 | RE (Green & Urban Spaces) | P.M JHK | 2023-08-08 | 2023-08-10
50 | Slow Progress Of Work and its Implication under the Condition of Contract | KPCIP/PMCSC/RE/ATD/Lot-1/113 | RE (Green & Urban Spaces) | P.D KPCIP | 2023-08-29
51 | Rate of Progress Pursuant to Sub-Clause 8.6 of GCC/PCC | KPCIP/PMCSC/RE/ATD/Lot-1/114 | RE (Green & Urban Spaces) | P.M JHK | 2023-09-19
52 | Submission of Recovery Working Schedule Under Sub-Clause 8.3 of GCC/PCC | KPCIP/PMCSC/RE/ATD/Lot-1/115 | RE (Green & Urban Spaces) | P.M JHK | 2023-09-28
53 | Response to notice under Sub -Clause 20.1 of Contract (To be read in conjunction with sub Clause 1.9,2.1 & 8.4 of COC) | KPCIP/PMCSC/RE/ATD/Lot-1/116 | RE (Green & Urban Spaces) | P.M JHK | 2023-10-04 | 2023-10-06
54 | Additional/Alternate Route to Redress the Grievance of the Vicinal Community | KPCIP/PMCSC/RE/ATD/Lot-1/119 | RE (Green & Urban Spaces) | P.D KPCIP | 2023-10-09
55 | Typical Construction Drawing of Public Washroom for Women in Old City Center Abbottabad | KPCIP/PMCSC/RE/ATD/Lot-1/118 | RE (Green & Urban Spaces) | P.M JHK | 2023-10-09 | 2023-10-10
56 | Typical Construction Drawing of Toilet Block-B in Sherwan Family Advanture Park | KPCIP/PMCSC/RE/ATD/Lot-1/117 | RE (Green & Urban Spaces) | P.M JHK | 2023-10-09 | 2023-10-10
57 | Typical Construction Drawing of Tuck Shop in Sherwan Family Advanture Park | KPCIP/PMCSC/RE/ATD/Lot-1/121 | RE (Green & Urban Spaces) | P.M JHK | 2023-10-10 | 2023-10-11
58 | Bunching of electrical cables in Bazar | KPCIP/PMCSC/RE/ATD/Lot-1/120 | RE (Green & Urban Spaces) | CEO WSSCA | 2023-10-10
59 | Proposed Electric Meter Panel Foundation | KPCIP/PMCSC/RE/ATD/Lot-1/125 | RE (Green & Urban Spaces) | CEO WSSCA | 2023-10-18 | 2023-10-18
60 | Providing & Fixing of Awning & Signage | KPCIP/PMCSC/RE/ATD/Lot-1/124 | RE (Green & Urban Spaces) | P.M JHK | 2023-10-18
61
62
63
64
65
66
67
68
69
70

## Out Going
Sr No. | Subject | Refrence | From | To | Date | Receiving Date | Source File
1 | Devlopment of Urban/Green Spaces and Parks Lot-1 Pedestiantsation of Old City Bazar & Devlpment of Sherwan Hill Park | CEO/WSSCA/023/8057 | CEO WSSCA | RE Green & Urban & PM JHK | 2023-01-25 | 2023-01-26
2 | Devlopment of Urban/Green Spaces and Parks Lot-1 Pedestiantsation of Old City Bazar & Devlpment of Sherwan Hill Park | CEO/WSSCA/023/8200 | CEO WSSCA | RE Green & Urban | 2023-02-22
3 | Request for No Objection Certificate For Conatruction Waste Disposal Site WSSCA's Response: | CEO/WSSCA/023/8250 | CEO WSSCA | PM. JHK | 2023-03-08 | 2023-03-10
4 | Request to Provide waste Container for Domestic Waste | CEO/WSSCA/023/8251 | CEO WSSCA | PM. JHK | 2023-03-08 | 2023-03-10
5 | Design Facilities in front of Sarafa Bazar | CEO/WSSCA/023/8330 | CEO WSSCA | RE Green & Urban | 2023-03-28
6 | Devlopment of Urban/Green Spaces and Parks Lot-1 Pedestiantsation of Old City Bazar & Devlpment of Sherwan Hill Park | CEO/WSSCA/023/8443 | CEO WSSCA | RE Green & Urban | 2023-04-19
7 | Slow Progress Of Work | CEO/WSSCA/023/8534 | CEO WSSCA | PM. JHK | 2023-05-16
8 | Observation on Interm Payment Certificate (IPC.1) Green/Urban Spaces Initiative KPCIP | CEO/WSSCA/023/------- | CEO WSSCA | RE Green & Urban | 0-05-23
9 | Devlopment of Urban/Green Spaces and Parks Lot-1 Pedestiantsation of Old City Bazar & Devlpment of Sherwan Hill Park | CEO/WSSCA/023/------- | CEO WSSCA | RE Green & Urban | 31/06/2023 | -
10 | Devlopment of Urban/Green Spaces and Parks Lot-1 Pedestiantsation of Old City Bazar & Devlpment of Sherwan Hill Park | CEO/WSSCA/023/8626 | CEO WSSCA | RE Green & Urban | 2023-06-08 | 2023-06-12
11 | Observations of CIU Team on Work Executed on Site | CEO/WSSCA/023/8645 | CEO WSSCA | RE Green & Urban | 2023-06-13 | 2023-06-15
12 | Request for issuance of NOC for Installation of Transformers and Electric Meters | CEO/WSSCA/023/8787 | CEO WSSCA | Chief Engr. (P&E) Pesco | 2023-07-27
13 | Devlopment of Urban/Green Spaces and Parks Lot-1 Pedestiantsation of Old City Bazar & Devlpment of Sherwan Hill Park | CEO/WSSCA/023/8816 | CEO WSSCA | RE Green & Urban | 2023-07-07
14 | The Engineer's Notification of Base Index rates 2for Adjustment for changes in cast under provisions of Sub-Clause 13.8,GCC | CEO/WSSCA/023/8822 | CEO WSSCA | D.T PMU KPCIP | 2023-07-10
15 | Bunching of electric cables in the Bazar | CEO/WSSCA/023/8837 | CEO WSSCA | RE Green & Urban | 2023-07-12
16 | Design Facilities in front of Sarafa Bazar | CEO/WSSCA/023/8982 | CEO WSSCA | RE Green & Urban | 2023-07-21
17 | Devlopment of Urban/Green Spaces and Parks Lot-1 Pedestiantsation of Old City Bazar & Devlpment of Sherwan Hill Park | CEO/WSSCA/023/9054 | CEO WSSCA | P.D KPCIP | 2023-08-09
18 | Provision of Technical Sanction (TS) of Awarded Sub-project under KPCIP | CEO/WSSCA/023/9061 | CEO WSSCA | RE Green & Urban | 2023-08-09
19 | Submission of Price Adjustment No. 1 (Covering IPC 01) | CEO/WSSCA/023/9062 | CEO WSSCA | P.D KPCIP | 2023-08-09
20 | Submission of Price Adjustment No. 1 (Covering IPC 01) | CEO/WSSCA/023/9058 | CEO WSSCA | Water supply & Sanitation Specilist PMU | 2023-08-10
21 | Design Facilities in front of Sarafa Bazar | CEO/WSSCA/023/9109 | CEO WSSCA | RE Green & Urban | 2023-08-24
22 | Request for approval of Facilities like Tennis Court,Gymnasuim and Summing Pool Under KPCIP | CEO/WSSCA/023/9117 | CEO WSSCA | P.D KPCIP | 2023-08-25
23 | Handing/taking of the left over inventory of the Chinese Camp at Sherwan Hill Park | ________________ | _________ | _________ | 2023-09-13 | 2023-09-14
24 | Provision of Technical Sanction (TS) of Awarded Sub-project under KPCIP | CEO/WSSCA/023/9210 | CEO WSSCA | RE Green & Urban | 2023-09-18
25 | Discrepancies in the Certified/ Paid Quantities of IPC-01 | CEO/WSSCA/023/9257 | CEO WSSCA | RE Green & Urban | 2023-09-28
26 | Reminder Regarding Designs of the Drainage and Zip lines | CEO/WSSCA/023/9270 | CEO WSSCA | RE Green & Urban | 2023-10-05 | 2023-10-05
27 | Bunching of electric cables in the Bazar | CEO/WSSCA/023/9274 | CEO WSSCA | RE Green & Urban | 2023-10-05 | 2023-10-10
28 | Providing and Fixing of Awning and Signage | CEO/WSSCA/023/9282 | CEO WSSCA | RE Green & Urban | 2023-10-09 | 2023-10-10
29 | Design of the Proposed Facility(Children Playing Area) in the Vacated Chinese Camp Site: | CEO/WSSCA/023/9281 | CEO WSSCA | RE Green & Urban | 2023-10-10 | -
30 | Bunching of electric cables in the Bazar | CEO/WSSCA/023/9294 | CEO WSSCA | RE Green & Urban | 2023-10-12 | 2023-10-17
31 | Reminder: Providing and Fixing of Awning and Signage | CEO/WSSCA/023/9295 | CEO WSSCA | RE Green & Urban | 2023-10-12 | 2023-10-17
32 | Technical Sanction of the project | CEO/WSSCA/023/9298 | CEO WSSCA | P.D KPCIP | 2023-10-12 | 2023-10-17
33 | Delay in Sharing of Complaints Registered in the GRC Register Placed on site | CEO/WSSCA/023/9319 | CEO WSSCA | RE Green & Urban | 2023-10-18 | 2023-10-20
34 | Discrepancies in the Certified/ Paid Quantities of IPC-01 | CEO/WSSCA/023/9333 | CEO WSSCA | RE Green & Urban | 2023-10-19 | 2023-10-20
35 | Alternate/Additional Route to Redress the Grievance of the Vicinal Community | CEO/WSSCA/023/9334 | CEO WSSCA | RE Green & Urban | 2023-10-20 | 2023-10-23
36 | Proposed Electric Meter Panel Foundation | CEO/WSSCA/023/9335 | CEO WSSCA | RE Green & Urban | 2023-10-20 | 2023-10-23