## Income
Sr No | Subject | Refrence | From | To | Date | Receiving Date | Source File
1 | Request for Umbrella NOC in respect of execution of mentioned sub-projects under KPCIP projects. | DD(Maint) /NHA/ATD/2022/190 | Ameer khan Dy.Director (Maint) NHA Abbottabad | Chief Executive Officer WASSCA | 2022-08-05 | 2022-08-11
2 | Request for Umbrella NOC in respect of execution of mentioned sub-projects under KPCIP LGE & RDD. | KPCIP/DT/MISC/2022-23/ 785-791 | Alamgir Afridi Water supply and Sanitation Specialist | Chief Executive Officer WSSCA | 2022-08-24 | 2022-08-26
3 | NOC's Updates status of the projects under KPCIP LGE&RDD. | KPCIP/DT/MISC/2022-23/ 1125-1127 | Alamgir Afridi Water supply and Sanitation Specialist | Chief Executive Officer WASSCA | 2022-09-20 | 2022-09-21
4 | Request for Issuance of Umbrella NOC in respect of execution of sub-projects under KPCIP. | DD(Maint) /NHA/ATD/2023/417 | Ameer khan Dy.Director (Maint) NHA Abbottabad | Chief Executive Officer WSSCA | 2023-06-13
5 | Shifting of Water Resorviors Locations. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-1/004 | RE (Water Supply) | Chief Executive Officer WSSCA | 2023-06-24
6 | Notice for commencement of works under sub-clause 8.1 of GCC/PCC. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-1/005 | RE (Water Supply) | M/S Zahir khan & brothers (ZKB) | 2023-07-27 | 2023-08-04
7 | Submission of contractor's representative in accordance with sub-clause 4.3 of GCC/PCC. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/006 | RE (Water Supply) | M/S Zahir khan & brothers (ZKB) | 2023-07-31 | 2023-08-04
8 | Submission pf (SSEMP) & (SSHSMP) IN Accordance with sub-clause 4.18 & 6.7 of GCC/PCC. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/007 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-08-02 | 2023-08-04
9 | Submission of detailed time programme/working schedule in accordance with sub clause 8.3 of GCC/PCC. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/008 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-08-02 | 2023-08-04
10 | Submission of records apropas contractor's personnel and equipment in accordance with sub clause 5.9 and 5.10 of GCC/PCC. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/009 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-08-02 | 2023-08-04
11 | Issuance of contruction drawing for water treatement plant. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/011 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-08-05 | 2023-08-10
12 | Minutes of meeting Dated 03-08-2023 | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/012 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-08-08 | 2023-08-10
13 | Impediments in carrying out construction activities in WTP area. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/016 | RE (Water Supply) | Chief Executive Officer WSSCA | 2023-08-25 | 2023-08-28
14 | Request for disassemble of pre-cast boundry wall (40 feet) installed bh PHE at the approach of access road to WTP. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/015 | RE (Water Supply) | Chief Executive Officer WSSCA | 2023-08-26 | 2023-08-28
15 | Submission of IFC drawings. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/014 | RE (Water Supply) | Chief Executive Officer WSSCA | 2023-08-26 | 2023-09-15
16 | submission of insurance polities as per the contract clause GCC/PCC 18 of the contract. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/027 | RE (Water Supply) | Project Director (PMU). | 2023-09-16
17 | Shifting and storingof PHED assets from chuna WTP site to identified neighborhood location. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/030 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-09-25
18 | Submission of quotation for conducting standard penetration test (spt) | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/028 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-10-04 | 2023-09-27
19 | Renevel of advence payment guarantee for OCB/KPCIP/02: Procurement of works for improment/contruction of WTP. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-1/008 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-10-03 | 2023-09-27
20 | Submission of retaining wall structure owing to loose fill and depressed levels at project site. | KPCIP/ZKB/ATD/LGE&RDD/2023/33 | PM Zahir khan & brothers (ZKB) | RE (Water Supply) | 2023-09-28 | 2023-09-18
21 | Submission of topographic cross section of 3 structures overlapping to privite property & submission of retaining wall structure owing to loose fill and depressed levels at WTP project site. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/029 | RE (Water Supply) | The Design Manager PMCSC-KPCIP | 2023-09-27 | 2023-09-27
22 | Submission of monthly progress reportunder clause 4.21 (progress reports) of GCC/PCC. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/033 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-09-27 | 2023-09-28
23 | Handing and taking of cut trees at WTP area. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/032 | RE (Water Supply) | Chief Executive Officer WSSCA | 2023-09-19 | 2023-09-28
24 | Submission of company profile for anti-termite source approval. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/034 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-09-19 | 2023-09-28
25 | Inventry of PHED assets (WTP Project) | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/036 | RE (Water Supply) | Chief Executive Officer WSSCA | 2023-09-19 | 2023-10-04
26 | Submission of 3x Financial quotatios for standard panatration test (SPT) at project site. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/035 | RE (Water Supply) | PM Zahir khan & brothers (ZKB) | 2023-09-18 | 2023-10-04
27 | Submission of Test Results/Reports for Construction Materials | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/038 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-12 | 2023-10-18
28 | Submission of Company Brochure & Sample for Water Stopper | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/039 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-12 | 2023-10-18
29 | Request for Removal of Tree Stems from project Site | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/040 | RE (Water Supply) | Chief Executive Officer WSSCA | 2023-10-16 | 2023-10-18
30 | Submission of design for "Project Information Board" | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/041 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-16 | 2023-10-18
31 | Submission of Standard Penetration Test (SPT) Report WTP Site | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/042 | RE (Water Supply) | Geo-Technical Expert, PMCSC-KPCIP, Peshawar | 2023-10-16 | 2023-10-18
32 | Minutes of meeting Dated 11-10-2023 | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/043 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-16 | 2023-10-18
33 | Non- Compliance under sub class 6.7 & 4.18 | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/044 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-20 | 2023-10-23 | incoming/ 33.pdf
34 | Discrepancy of Steel DIA's in Construction drawing & their market availability | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/045 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-23 |  | incoming/ 33.pdf
35 | Contractors authorized representative deputy project manager (DPM) | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/048 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-24 |  | incoming/ 33.pdf
36 | Submission of detailed time programme/working schedule in accordance with sub clause 8.3 of GCC/PCC. | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/049 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-24 |  | incoming/ 33.pdf
37 | Submission of Steel MTC/Brochure for approval | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/050 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-24 |  | incoming/ 33.pdf
38 | Submission of Corporate company profile of FF Steel | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/051 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-25 |  | incoming/ 33.pdf
39 | Submittal of Cement MTC/Brochure for Approval | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/052 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-24 |  | incoming/ 33.pdf
40 | Submission of Company Brochure of "Decora" for water stopper | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/053 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-25 |  | incoming/ 33.pdf
41 | Submission of Company Brochure and Sample for water Stopper | KPCIP/PMCSC/RE-ATD/CW-02/Lot-2/054 | RE (Water Supply) | ZKB-M/S T.T SH-INSAAT LIMITED LIBALITY COMPANY (JV) | 2023-10-25 |  | incoming/ 33.pdf
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57

## Out Going
Sr No | Subject | Refrence | From | To | Date | Receiving Date | Source File
1 | Request for issuance of umbrella NOC for laying/installation of main water supply line. | CEO/WSSCA/023/8056 | Chief Executive Officer WSSCA | Director General GDA | 2023-01-25 | 2023-01-26
2 | Extension of jica gravity water supply scheme Abbotabad Water supply pipe line distribution network contradiction in the designed drawing and on ground position at outlet pipe of WTP. | CEO/WSSCA/023/8526 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-05-15
3 | Request for Umbrella NOC in respect of execution of mentioned sub-projects under KPCIP projects.- Provisional payment of OFC required for processing of NOC. | CEO/WSSCA/023/8525 | Chief Executive Officer WSSCA | Project Director (PMU). | 2023-05-15 | 2023-05-15
4 | Requirements of funds for payment of land compensation in water supplyproject under KPCIP. | CEO/WSSCA/023/8550 | Chief Executive Officer WSSCA | Project Director (PMU). | 2023-05-24
5 | Extension of jica gravity water supply scheme Land Acquisition for water supply line-acknowledgement required for 2200m long water supply route from jandar baari to phalkot mosque. | CEO/WSSCA/023/8609 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-06-06
6 | Extension of jica gravity water supply scheme Abbotabad Water supply distribution network contradiction -test pits at KKH-N35 | CEO/WSSCA/023/8608 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-06-06
7 | Extension of jica gravity water supply scheme Abbotabad provisional layout of the pipeline passing along the C&W roads. | CEO/WSSCA/023/8610 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-06-06
8 | Extension of jica gravity water supply scheme Abbotabad Land Acquisition for water supply line- hurdles in the pipe line route at outlet (Choona WTP). | CEO/WSSCA/023/8607 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-06-07
9 | Information - NOC fee deposit in prescribed bank account - NHA islamabad. | CEO/WSSCA/023/8633 | Chief Executive Officer WSSCA | Deputy Director (maintenance) NHA | 2023-06-09 | 2023-06-12
10 | Unavoidable Issue in land acquisition from jandar baari to phalkot Mosque shifting of 2200 meters pipeline route towards moza maalsa side. | CEO/WSSCA/023/8639 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-06-12
11 | Water supply distribution network shifting of water resorvoirs location. | CEO/WSSCA/023/8640 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-06-12
12 | Request for issuence of NOC in respect of execution of sub-projects under khyber pakhtubkhwa city improment project (kpcip). | CEO/WSSCA/023/8665 | Chief Executive Officer WSSCA | Deputy Director (maint) NHA | 2023-06-16 | 2023-06-19
13 | Extension of jica gravity water supply scheme Abbotabad shifting of water resorvoirs location. | CEO/WSSCA/023/8789 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-06-27
14 | Extension of jica gravity water supply scheme Abbotabad provisional layout at N35 section. | CEO/WSSCA/023/8823 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-07-10
15 | Extension of jica gravity water supply scheme Abbotabad Re:approval of option 2 main distribution pipe route. | CEO/WSSCA/023/9083 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-08-16 | 2023-08-17
16 | Request for approval of carrying out test pits at specified locations. | CEO/WSSCA/023/9082 | Chief Executive Officer WSSCA | Deputy Director (maintenance) NHA | 2023-08-16
17 | Note for records meeting with superintendent engineer PHED - Abbottabad. | CEO/WSSCA/023/9105 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-08-23
18 | Shifting and storing of PHED assests from choona WTP site to identified neighborhood locations. | CEO/WSSCA/023/9224 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-09-19
19 | Request for NOC for proposed tank no 8, shimla/nullah tank (100,000 gallons) - uc malakpura. | CEO/WSSCA/023/8981 | Chief Executive Officer WSSCA | Tehsil muncipal officer | 2023-09-20 | 2023-07-24
20 | CW_02-LOT 1 (Abbotabad) - suggestion to pause the commencement | CEO/WSSCA/023/9254 | Chief Executive Officer WSSCA | Director technical KPCIP-PMU | 2023-09-20 | 2023-09-28
21 | Comments Matrix - chuna WTP. | CEO/WSSCA/023/9235 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-09-27
22 | Cutting of trees from construction of site of WTP without securing NOC from the forest department. | CEO/WSSCA/023/9249 | Chief Executive Officer WSSCA | Project Director (PMU). | 2023-09-28
23 | Re- handling &taking over of cut trees at water treatement plant | CEO/WSSCA/023/9262 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-09-28
24 | Comments matrix sheet - chuna WTP | CEO/WSSCA/023/9235 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-09-28
25 | Request to attend the meeting regarding reservations on KPCIP WTP - Abbottabad | CEO/WSSCA/023/9273 | Chief Executive Officer WSSCA | Executive engineer (Bulk Division) PHED | 2023-10-03
26 | Reminder - response Awaited Comments matrix sheet | CEO/WSSCA/023/9284 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-05 | 2023-10-10
27 | Note for records -- Field visit of PMCSC design team to qualify the transmission line | CEO/WSSCA/023/9283 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-09 | 2023-10-10
28 | Follow up - Awaited review and feedback for notified issues. Cw-02 lot 01 | CEO/WSSCA/023/9255 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-10 | 2023-10-04
29 | Follow up - Awaited review and feedback for notified issues WTP Outlet trick | CEO/WSSCA/023/9256 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-12 | 2023-10-04
30 | Technical section of the project (CW-02 LOT-01) | CEO/WSSCA/023/9297 | Chief Executive Officer WSSCA | Project Director (PMU). | 2023-10-12
31 | Technical section of the project (CW-02 LOT-02) | CEO/WSSCA/023/9296 | Chief Executive Officer WSSCA | Project Director (PMU). | 2023-10-12
32 | Minutes of coordination meeting held in WSSCA OFFICE ON 10-10-2023. | CEO/WSSCA/023/9296 A | Chief Executive Officer WSSCA | Superintendent engineer PHED | 2023-10-12
33 | Using of PHED premies as entry way for distribution chember (Raw water inlet) | CEO/WSSCA/023/9316 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-18 | 2023-10-19
34 | Re 2. Intimation of the competent Authority for Handling / taking over the trees | CEO/WSSCA/023/9318 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-18 | 2023-10-20
35 | RE - Design finalization: location of intake structure for jica water supply extention scheme | CEO/WSSCA/023/9339 | Chief Executive Officer WSSCA | Project Director (PMU). | 2023-10-23
36 | Re- handling &taking over of PHED Assets Present in KPCIP-WTP site | CEO/WSSCA/023/9268 | Chief Executive Officer WSSCA | Executive engineer (Bulk Division) PHED | 2023-10-05
37 | KPCIP Abbottabad | CEO/WSSCA/023/9269 | Chief Executive Officer WSSCA | Executive engineer (Bulk Division) PHED | 2023-10-05
38 | Restoration of the access road after completion of KPCIP-WTP | CEO/WSSCA/023/9271 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-05
39 | CW_02-LOT 1 Missing specification of MS Pipe | CEO/WSSCA/023/9395 | Chief Executive Officer WSSCA | RE (Water Supply) | 2023-10-31